## Results frame work
Goal | Impact Indicator | MoV | Target | Responsibility | Target Date | Risks | Assumptions
Improved dietary behaviours among Sri Lankan Population by 2025 | 1.% of population consuming recommended food plate | Dietary and KAB Survey Baseline by August 2021 Follow up Survey Aug 2026. Photos of meals (Mc Gill University method) | 50% of the population consume meals according to recommended food plate (with recommended servings of food). Each year starting 2021) 25% of Households, 50% of meals, 2022) 25% of Households, 75% of meals, 2023) 50% of households 50% of meals 2024) 50% of households,75% of meals | Nutrition Division | 2025 | Natural Disasters/disease outbreaks/ poverty will reduce food security | 1. People may have awareness on healthy eating 2.Political Commitment for nutrition improvement continues3. Budget Allocation/Donor Funding available for programmes
| 2.% of population not exceeding RDA on sugar, salt, fat(SSF) | Same as above | 50% of adult population reduce consumption of SSF to the recommended level | Nutrition Division | 2025
| 3.% Children consuming minimum acceptable diet, minimum meal frequency | Same as above | 1.90% of children below 5 years of age will have minimum acceptable diet2. 90% of children below 5 years of age will have minimum meal frequency | Family Health Bureau, Department of Census & Statistics(DHS) | 2025
| 4.Related policies and plans updated based on FBDGs for the provision of larger quantities of critical food of good quality and required levels of safety | Policy documents | At least 75% of required policies are amended or incorporated FBDGs | Ministries of Agriculture, Health, Fisheries, Animal Production, Internal Trade, Finance, Rural Economy, Social empowerment | end of 2022 | Ministries will have competing work | Relevant ministries agree on incorporating and monitoring outcomes
Outcomes/ outputs | Outcome Indicator | MoV | Target | Responsibility | Target Date | Risks | Assumptions
Outcome 1: Policy and regulatory environment in place to drive forward the Food Based Dietary Guidelines (FBDGs) making safe and quality food availble | 1.Number of associated regulations - regulatory and fiscal Gazetted/updated/amended and newly drafted and passed which are Gazetted | Gazettes/ Desk reviews | required regulations are amended or formulated | CFA and Food control Administration Unit of the MoH (FCAU) | End of 2023 | Departments will have other priorities | Regulatory mechanisms strengthened
| 2.Number of regulations enacted addressing food regulatory needs of the country | Reports of Food Inspectors islandwide | Frequency increased by 25% | CFA and FCAU | end 2021 | Medical Officers of Health(MOOH)/Food and drug inspectors(FDIs)/ Public Health inspectors (PHII) will have other priorities | Mooh, FDII,PHII may increse frequecncy of raids and law enforcement
| 3. Frequency of enforcing key regulations related to food safety | Reports from NFA
Output 1.1 Food Act and associated regulations enacted | 3. Availability of functioning mechanism for chemical and microbiological testing targeting food supply chain (food production, processing plants, formal and informal food vendors) | MIS for food supply chains , Review Reports Gazetted regulatins, Documents of implementing authorities: e.g. list of violations and actions taken, reports of law enforcement | Regulations on: food labeling, food advertisement, BF code, food safety for restaurants and eateries, commercially prepared or processed food food imports and standards and other Food Act related regulations are in place and enacted | Chief Food Authority, FCAU | End of 2023 | No obstruction because of conflicts of interest by business community
Activities | Indicator | MoV | Target | Responsibility | Target Date | Risks | Assumptions
1.1.1 Study the performances related to the implementation of the food act and regulations, e.g. violations and action taken (Food Standards 1989 defines standards for all food groups) | Performance levels of enforcement services; (measure speed and accuracy of enforcement) | FCAU quarterly performance report Success stories, achievements and review of reports. | 80% | Chief Food Authority (CFA) and the Food Advisory Committee and SLSI) | End 2021
1.1.2 Formulation and publication of Gazette notifications necessary regulations/ enactment of existing reguations addressing; (a) Food Supplements and nutraceuticals (b) Novel foods (c) Organic food, (d)SFF and Trans Fats in food (e)Antibiotic Residues in Food (f) Pesticide Residues in food (g)Contaminants in food | Number of Gazetted Regulations | Food Control Administration (FCAU) supervisory reports, data published in FCAU Web page Same as above | 50% end 2021 , 75% end of 2022, 100% by 2023 | Authorized officers and CFA | End of 2023
1.1.3 Revision of existing food regulations/ standards (eg: Colour Coding for Sugar levels) | 1. % revised reulations/standards out of of those requiring revision | Revised regulations/standards | 50% mid 2021 , 100% End of 2023 | Authorized officers and CFA | End of 2023
1.1.4 Introduction of a feedback mechanism (to obtain , complaints and suggestion related to food safety issues) from consumer groups, research groups and general public | 1. Number and spread of consumer groups (watchdogs) to identify regulatory oversight and negligence. 2. Number and spread of research groups from Universities and research Institutes 3. The number and type of complaints received by The CFA and FACU | 1. Register of consumer groups registered at Consumern Affairs Authority (constitution as per CAA) 2. Register of Research groups registered at FACU 3.Reports of Complaints and Actions taken from database of FACU | 1.At least one Consumer Group registered at each District 2. At least one watchdog research group registered per University having faculties in food and agriculture | Consumar Affairs Authority (CAA), CFA and FACU | 1.All consumer groups formed by mid 2021 2. All research groups formed by end 2021
1.1.5 - Establishment of a responsive, outcome-oriented, predictable, risk-proportionate, and independent regulatory system. | Availabity of an independent regulatory system which is outcome-oriented (focusing on food safety outcomes), predictable based on the best scientific evidence, risk-proportionate based on threat to public health and with responsiveness (with ability to respond rapidly to a crisis, contain and correct any food safety lapse that has occurred in order to minimize health effects.). | Reports prepared by FCU with guidance of CFA. Report should be based upon the indicators listed and should be submitted every 6 months. | Strengthen and reorient exisiting system | Ministry of Health, Ministry of Science and Technology, Ministry of Local Government, Min istry of Internal Trade | by end of 2022. | 1. Lack of resource allocation 2. Change in Ministry portfolios | That decision makers have a thorough understanding of regulatory Affairs
Output 1.2 Relevant Fiscal Policy changes done to facilitate people to access food according to FBDGs
Activities | Indicator | MoV | Target | Responsibility | Target Date | Risks | Assumptions
1.2.1 Taxes imposed on unhealthy foods such as confectionary both imported and local | 1. Healthy and unhealthy foods listed according to available classifications 2.% of unhealthy items listed with increased taxes | Information from Dept of Inland Revenue and trade and fiance | 1. Healthy and unhealthy food in the market classified 2.Taxation of unhealthy food items increased | Ministry of Finance, Trade | 1. List of healthy and unhealthy food made available by31st March 2021. 2. nterministerial dialogue to be carried out to impose taxes for unhealthy food items- May 2021. 3. Taxation to be determined by budget 2021 | Lack of coorporation for imposing taxes due to various matters | Government agrees to decrease the availability of unhealthy food in the market by imposing taxes and increasing healthy by providing subsidies
1.2.2 Subsidies provided for growing organic, nutritious food crops and production of healthy food items | 1. Number of healthy food items which received subsidies for productionannually 2.number of healthy food items with reduced prices 3. Number of healthy food items with increased volume available in the market | 1. Information from Dept of Inland Revenue, HAARTI, Ministries of Trade and finance 2. List of Healthy fresh and dry food items listed | At least 50% of healthy food list received subsidies by 2025 | Ministry of Agriculture, live stock, trade and finance | 1. Interministerial dialogue to be carried out by thethird quarter of 2021. 2.Subsidies to be determined by budget 2021 | Lack of coorporation for imposing taxes due to various matters | Government agrees to decrease the availability of unhealthy food in the market by imposing taxes and increasing healthy by providing subsidies
1.2.3 Tax exemption for healthy food production | 1.Number of healthy food items with reduced prices /annum 2. Value of subsidies provided for healthy food production | Information from Dept of Inland Revenue, HAARTI, Ministries of Trade and finance | Tax is reduced for at least 25% of healthy food list received by 2025 | Market information from HARTI, Wholesale markets, supermarkets, open markets, retail shops, Ministries related to food production and processing, food processors association | 1. Interministerial dialogue to be carried out by thethird quarter of 2022. 2.reduction of taxation to be determined by budget 2022 | Lack of coorporation for imposing taxes due to various matters | Government agrees to decrease the availability of unhealthy food in the market by imposing taxes and increasing healthy by providing subsidies
1.2.4. Regulating food prices coordinated with supply and demand | 1. Food price anomalies 2. Strategy on food pricing in line with supply and demand made available | Food price reports through all media
Output 1.3 Policies formulated and acted upon for improved health among school children ( for behaviour change programs refer to Setting on School, Univerities and Colleges) | 1. Policies, Strategies and Programs including the intention to improve nutrition and stating associated activities eg: National Nutrition Policy, National Health Policy,School Health Policy, Education Policy. Education for All document, | Perusal of these documents
Activities
1.3.1 Health and Physical education curriculum revised in line with health, food and nutrition policies and FBDGs - TO BE SHIFTED TO SETTINGS | 1. Number of revised curriculae which incorporate health, food and nutrition policies and FBDGs | Relevant curriculae | Secondary School curriculum, curriculae to train primary health care staff and teacher training curriculae revised incorporating health, food and nutrition policies and FBDGs by 2022 | Ministry of Education, Ministry of Health (ET&R, NIHS), Ministry of Sports | end 2022 | Relevant authorities do not revise curriculae during target period
1.3.1.Lobby for following school canteen guidelines and activity guidelines | 1. Number of ministry websites which published canteen guidelines published 2. % incorporated canteen guidelines into canteen supplier tender documents 3. % schools with feedback mechanism on food established at the canteen | School canteen guide and relevant documents, reports, compliance checks, feedback reports | School canteen guide and school activity guides Incorporated into all education and training Policies and Strategic plans | MoE, MoH, MoHE | 2022
Outcome 2: Communities are knowledgeable about a minimum of 5 of the FBDGs (Behaviour Change) SEE SETTINGS IN IMPLEMENTATION PLAN. THIS WILL START FROM OUTPUTS |  | Random Survey of knowleedge | At least 1 member in 80 % of Households know at least 5 FBDGs | HPB, Nutrition Division, RDHSs, MOHs, Village level officers (set of 5) and FBDG Implementation Committee comprsing of representatives from Education, Information and Media, private media institutions, Home Affairs, Local Government, Sports, Producer and Trader Organizations, Universities, | 1) mid 2022 2) mid 2023 3) mid 2024 4) mid 2025 - Baseline Dietary Intake Study to be completed by end 2021
| Proportion of population aware of FBDGs (%) | KAB Survey (to be completed by mid 2021) | 75% of people to be aware | Same as above | by end 2021
Outcome 3: Safe and quality nutritious food adequately available for the community at affordable prices | 1) % of Meat, fish, eggs, fruit, vegetables, nuts and oil/fat,cereals, yams,dairy products, pulses available in the required quality, quantity and safe levels 2) Prices of essential food items | Production figures published by HARTI, Ministries of Fisheries and Livestock and other Trading bodies | 1) 80% of food available I the market are in optimal requirement 2) 100% of optimal requirement | Ministries related to food production and food security, Food Processors, Food importers, FCU, CAA, CFA | 1) by mid 2022 2) by mid 2024
Outputs |  | MoV | Target | Responsibility | Target Date | Risks | Assumptions
3.1 Food Testing Laboratories increased around the country | 1. Number of newly established food laboratories in the country | Databases of ministries, semi government & private organizations | Adequate reliable food testing facilities are available in the country | MoH, MoA, MoF | 2025
3.2 Existing storage systems to be strengthened with cold storage facilities | No of existing warehouses upgraded from national to Divisional level | Records and Inventory of Food Commissioner | 100% of need | Ministries and Departments responsible for food security and food production, Chambers of Commerce, Producer and Trader Associations | 2023
3.3 Agricultural produce is in line with nutrition and safe food requirements of the population (nutrition sensitive safe agriculture) | Profile of agricultural produce | Production reports
3.4 Convenience and other pre- prepared food processors offer healthier food (less sugar, salt and fat) | Improved food composition, less additives etc
Note on A7: Visakha: Better to drop contribute and say
Note on A27: Visakha: Again no outputs. Disjointed. Implementattion plan has some of the activities and outputs but no outcomes. So the two tables do not have much coherence.
Note on A29: Visakha: Where are the outputs and how can we drive the required quantities of food production in a nutrition seelsivie manner. Activities are also far from adequate.
Note on B5: Visakha: This is not related to the goal. Shpuld be an output indicator

## iMPLEMENTATION PLAN
Outcome 2: Communities are knowledgeable about a minimum of 5 of the FBDGs and apply this knowledge to improve their food related behaviour (Behaviour Change)
Partial or intermediate outcomes | Outputs ( to be in product language in the past tense) | Activities ( should be detailed out on how to reach and deliver outputs) | Target groups /Settings | Level of implementation (Central/Provincial/District/Divisional) | No of Programmes/Activities | Lead ministry/ Organizations | Other Ministries/ organizations | Time to be completed | Estimated Budget Rs | Source of funding | Mode of dissemination (to be clear - communication method) | Existing tools / New tools to be developed | Indicators | Outputs | Methods of verification | Responsible monitoring organizations | Frequency of monitoring (Annually/Quarterly etc.) | No: of programmes to be completed within identified period | Risk | Assumptions
HEALTH SETTINGS
Support from health administrators to implement FBDG achieved. | Advocacy programme - 1. Launch of FBDG completed 2. Legislations against promoting unhealthy food and beveragers for children. Trainers Manual updated - this is an output |  | Health administrators and policy makers (preventive, curative and aryurveda) | Central (HDC, HoD and Provincial commissioner meetings of Indigenous Medicine ) | At least 4 programmes within two years | MoH (ND) | Ayurveda department | 2021-2022 | 200000 | GOSL/FAO | Advocacy programmes | Advocacy packages, Trainers mannual | Number of Advocacy programmes conducted out of scheduled | All scheduled programmes completed | Minutes | MoH (ND/HPB) | Annualy | 1 4 | Inability for advocacy due to compacted Schedules in administrators meetings | Will have opportunites to advocate administretors in their meetings
Technical Health staff improved their knowledge on FBDGs and healthy eating | FBDG Awareness programmes completed |  | Technical heads of health units government and private (preventive and curative) and Indigenous Medicine hospitals/Relevant Health professional colleges | Central | At least 2 programmes within two year | MoH (ND) | Government and Private Hospitals/Ayurveda department | 2021-2022 | 300000 | GOSL/FAO/WHO/WFP | Lectures/Group works/Role-play | taining modules and trainnig guides | 1. Number of participants trained. 2. Percentage of Knowledge improvement among participants | All scheduled programmes completed | Pre & Post test evaluation reports | ND/HPB | Bi-annualy | 2 | Emergency situations, Time constrains | Could conduct online training if training in person would not be possible
| TOT (master trainer programme) completed |  | National level technical heads/consultants (Health and Indigenous Medicine/preventive and curative) | Central | At least 2 programmes within two year | MoH (ND) | Health departments and Ayurveda departments. | 2021-2022 | 200000 | GOSL/FAO/WHO/WFP | Lectures/Group works/Role-play | taining modules and trainnig guides | 1. Number of participants trained. 2. Percentage of Knowledge improvement among participants | All scheduled programmes completed | Pre & Post test evaluation reports | ND/HPB | Bi-annualy | 2 | Emergency situations, Time constrains | Could conduct online training if training in person would not be possible
| completed (master trainer programme) |  | District level technical officers(CCPs, MO MCH, MO NCD, MO Nutritrion) | Central | At least 2 programmes within two year | MoH (ND) | Provincial and District health authorities | 2021-2022 | 200000 | GOSL/FAO/WHO/WFP | Lectures/Group works/Role-play | Taining modules and trainnig guides | 1. Number of participants trained. 2. Percentage of Knowledge improvement among participants | All scheduled programmes completed | Pre & Post test evaluation reports | ND | Annualy | 2 | Emergency situations, Time constrains | Could conduct online training if training in person would not be possible
| Training programs for divisional health staff through identified district working group (CCPs,MO MCH,MO NCD, MO Planning) completed |  | MOH /CMO (ayurveda), relevant curative sector MOs (Medical wards, OPD)and area GPs (preventive and curative) MOIC PMCU,MO HLC | Provincial/District | At least one programme per district per year | District health authorities/RDHS (Master trainers at th district level PD/RD) | Hospital directors (Health and Indigenous medicine) | 2021-2025 | 1000000 | GOSL/FAO/WHO/WFP | Lectures/Group works/Role-play | Taining modules and trainnig guides/video clips/ face book page/small interactive clips for sharing and tagging | 1. Number of participants trained. 2. Percentage of Knowledge improvement among participants | All scheduled programmes completed | Pre & Post test evaluation reports | RDHS/MO-MCH | Annualy | 125 | Emergency situations, Time constrains | Could conduct online training if training in person would not be possible
| Training sessions of grass-root level officers completed during monthly conferences |  | PHM/PHI | Divisional | 5 training programmes per year (Training on one prioritized message per month to improve their knowledge on 5 prioritized messages per year.) | MOH /CMO (Ayurveda) |  | 2021-2025 |  | GOSL | Lectures/Group works/Role-play | Taining modules and trainnig guides/video clips/ face book page/small interactive clips for sharing and tagging/WhatsApp, Messanger | 1. Number of participants trained. 2. Percentage of Knowledge improvement among participants | All scheduled programmes completed | Pre & Post test evaluation reports | MO-MCH Annual Field level supervision by Nutrition Division | Quartely | 25 programmes per MOH for 5 years | Emergency situations, Time constrains
Community is aware on FBDGs and healthy eating | Awareness programs completed on FBDGs |  | Mother support groups/ Happy villages/CBOs | MOH level (Divisional) | 2 programmes per year in each PHM area | Divisional Health Authorities | Divisional Indigenous medicine authorities | 2021-2025 |  |  | Food demonstrations, Exhibitions, Healthy food fairs, Lectures | IEC materials, Nutrition education modules, Healthy food plate models | Number of awareness programmes conducted | Awareness programmes conducted in each PHM area as per schedule | Reports from divisional health authorities, PHM dairies | Divisional health authorities | Bi-annualy | Depending on the number of PHM areas | Work overload, Poor fuctional MSGs | Free of time constrains and Availability of well functioning MSGs and CBOs
| Awareness programmes for school children and hospital community completed |  | Students and Patients | Provincial/District/Divisional | At least one programme in each school annually | Divisional Health Authorities | Divisional Indigenous medicine authorities | 2021-2025 |  |  | Food demonstrations, Exhibitions, Healthy food fairs, Lectures | IEC materials, Nutrition education modules, Healthy food plate models for school children | Number of awareness programmes conducted | Awareness programmes conducted in each PHI area as per schedule | Reports from divisional health authorities, PHI dairies | Divisional health authorities | Bi-annualy | Depending on the number of schools | Time constrains | School authorities alocate time for awareness programmes
| Awareness programmes on healthy food completed |  | Food manufactures and Hotels | Provincial/District/Divisional | Two programmes per year in each PHI area | Divisional Health Authorities | Divisional Indigenous medicine authorities | 2021-2025 |  |  | Food demonstrations, Exhibitions, Healthy food fairs, Lectures | IEC materials, Nutrition education modules, Healthy food plate models | Number of awareness programmes conducted | Awareness programmes conducted in each PHI area as per schedule | Reports from divisional health authorities, PHI dairies | Divisional health authorities | Bi-annually | 10 Programmes conducted in each PHI for 5 years | Work overload, Time and funding constrains | Free of time and funding constrains
| Grading system in place for school canteens and other food establishments based on healthy food |  | Food manufactures, school canteen owners and food establishment owners | Provincial/District/Divisional |  | Divisional Health Authorities |  | 2021-2025 |  |  |  | Guidelines and Grading tools | Number of food establishments with improved grading | Food establishments improved their grading | Reports from divisional health authorities | Divisional health authorities | Annually | Depending on food establishments/schools in the area | Poor attitudes, Resourse constrains | Supportive behaviours of food establishment owners and staff to impove their standards
EDUCATION SETTINGS
All pre-school and school children received nutrition in pre-schools and schools | Advocacy for responsible educational authorities to provide nutritious meals at pre-schools and schools and to incoperate it to early childhood development policy and eduction policy |  | Educational authorities | Central | 1 | MoH (ND/HPB) | Education, Women and Child affairs | 2021 |  |  | Advocacy programmes | Advocacy packages, Trainers mannual | Scheduled Advocacy programme conducted | Agreement of relavent authorities to provide nutritious meals for pre-school and school children | Minutes | MoH |  |  | Resource constrains | co-operation of relavent authorities for provision of nutritious pre school and school meals.
Healthy eating is promoted through implementation of pre-school and school meal standards and school canteen guidelines | School meal standards revised and disseminated based on FBDGs to ensure nutritious food at pre-schools and school( including lunch boxes sent from home and also food prepared for/brought in for celebrations, fund-raising, fairs and events especially sports events and school canteens) |  | Pre-school and School management, school canteen owners and Parents | Central | 3 consultative meetings | MoH (ND) | Education, Women and Child affairs | 2021- 2022 | 100000 | GOSL | Advocacy programmes for Principals in education zones | Pre-school and school meal standards | 1. All scheduled consultative meetings conducted. 2. Number of canteens adopted to FBDGs | Availability of meal standards for; 1. Pre-schools 2. Schools | Minutes | MoH | Anually | 3 | Lack of resources | Free of resource constrains
| 1.Baseline assesment on the existing mechanism and gap identification 2. Establishment of Nutrition freindly pre schools - Eg: 'poshana mithuru pera pasala' 3. Reinforcement of healthy eating at school 4. Develope sample menues |  | Pre-school management, school canteen owners and Parents | Divisional | 1 training programme per educational zone/division per year | Child secretariat, Zonal education authorities | Divisional health and Indigenous medicine authorities | 2021-2025 | 50,000 per Zone | GOSL | Teacher training, perents training, cooking demonstrations | Grading and rewarding tools, Sample menues, School canteen survey reports | 1. All scheduled training programmes conducted. 2. Number of training programmes conducted 3. Percentage of teachers trained out of all teachers 4. Number of parents trained in pre-schools and schools 5. Percentage of pre-schools, schools adopting developed sample menues out of al pre-schools and schools in the area | Nutrition friendly pre-schools and schools established | 1. Baseline survey and periodical surveys 2. Database of pre-schools and schools (Government, semi government, Private and International) 3.Supervisions/Observations of pre-schools and schools | Divisional secretariat/Zonal educational authorities | Quarterly | 5 training programme per educational zone/division and supervision of all pre-schoolsand schools | Lack of interest and Poor monitoring | All pre-schools and schools are adhered to meal standards
| 1. Revise the pre-school and school teacher training modules incooperationg FBDG 2. Incooperate revised FBDGs into school curriculums of all grades |  | Curicullum developers | Central | 1. Three consultative meetings 2. Three consultative meetings | National Institute of Education (NIE), Vocational training, Higher education | MoH | 2021-2025 | 50,000 per programme | GOSL | Interactive activities | Curriculae | All teacher training curicullae and school curicullae revised | FBDGs are incooperated in to all teacher training curicullae and school curicullae | Revised curicullae | Child Secretariat, Education Ministry | at the end of 2025 | 6 programmes | Time constrains | Support from relevant stakeholders gained.
Healthy eating is promoted through implementation of pre-school and school gardening | Streamline nutirition sensitive school gardening from pre-schools through secondary schools (government, semi-government, private, international) |  | Students | Divisional/Zonal |  | MoE, Child secretarist, Divisional authorities | Agriculture | 2021-2025 |  |  | Training, School club activities, Competitions, Food fairs | IEC materials, Health promoting school criteriae to include nutrition sensitive school gardening | Proportion of nutrition sensitive pre-school/school gardens out of all in the area | All schools adopted nutrition sensitive school gardening | Supervision and monitoring | MoE, Zonal educational authorities | Annually |  | Poor compliance, Time constrains, Lack of resources | All pre-schools and schools are compliant to nutrition sensitive school gardening.
Healthy eating is promoted through healthy food environment | 1.Conduct a baseline survey on meals provided for the student from neighbourhood food establishments 2. Develop canteen guidelines for vocational training institutes, Universities, other higher edcuational institutes and unregulated education settings (Private tution) 3. Training and awareness of administrators, staff and canteen owners of higher educational institutes |  | vocational training institutes, Universities, other higher edcuational institutes and unregulated education settings (Private tution) | Central | Depending on the number of institutions | Ministry of education / higher education/vocational training | MoH | 2021-2023 |  |  | 1. workshops 2. competitions 3. healthy food fair 4.demonstrations 5. posters and leaflets | Nutrition education Modules, | 1. Baseline and periodical surveys conducted 2. Canteen guidelines for higher educational institutes developed 3. Number of training programmes conducted | Knowledge on FBDGs and dietary behaviours improved among students, staff, management and canteen owners of higher educational institutes | Survey reports, Supervisions and Observation reports | Vocational training, Higher education ministry | Bi-annually | Depending of the number of institutes | Difficulty in approaching neighbourhood food outlets of private tution classes and higher education institutes | All food establishment owners are compliant to guidelines.
| Social behaviour change communication |  | School community | Central, Provincial, Distrct | 1 Social marketing campaign | MoH (HPB/FHB/ND) | MoE, Child Secretariat, Higher Education, Vocational training | 2021-2025 | 5000000 | GOSL, Development agencies (WHO/WFP/FAO) | Social marketing campaign | Videos, TV Spots | Social marketing campaign implemented | Knowledge on FBDGs and dietary behaviours improved smong school community | Surveys | MoH (HPB/FHB) | At the end of the 2025 | 1 | Financial constrains | Resources can be obtained.
Food Services
Support from food industry to change the population dietary behaviours through implementation of FBDG is achieved. | Advocacy programs completed for food industry |  | 3.Owners/Management of food industries (Large/Medium/Small scale), Food Importers, Tourist board | Central/Provincial/District/Divisional | Depending on the number of food industrues in the area | Health | Trade, Finance, Industry and Commerce, Department of Custom, Consumer affairs | 2021-2022 |  | GOSL/FAO | Advocacy programmes | Advocacy packages, Policies, Guidelines and Standards, Gazette notifications | Number of Advocacy programmes conducted out of scheduled | All scheduled programmes completed | Minutes | MoH | Annually | Depending on the number of food industrues in the area | Conflict of interest | co-operation of relavent authorities for provision of nutritious foods for the community
| TOT programmes/Training programmes on healthy food preparation and handling (Storage, Packaging and Distribution), national policies, food regulations and standards |  | Instructors at Hotel schools, Vocational Training centers, University, Agriculture, Livestocks and Fisheries | Central/Provincial/District/Divisional | Depending on the number of food industrues in the area | MoH | Higher education, Vocational training, Agriculture, Livestocks and Fisheries, | 2021-2025 |  |  | Chef-curriculum development/Food technology curricullum, University curricullum/Introducing food plate concet and healthy food corners (Healthy food range) | Curriculum development workshops/FBDGs trainers manual/Preand Post test evaluation tools | 1. Number of curricullum revised 2. Percentage of knowledge improvement among participations | FBDGs are incooperated in to training curricullae | Training curriculae | Higher education, Vocational training, Agriculture, Livestocks and Fisheries, | Annually | Depending on the number of industitutions | Non-compliance | All institutions agreed to train their students on FBDGs and healthy food services
Support from food industry to establish healthy food environment | Grading system for healthy foods and food establishments put in place |  | Food inductries including formal and informal food services, food outlets, super markets, Milling industries including spoces and condiments producers, Online food traders | Central | 10 Consultative meetings and 3 consultative workshops | MoH (FCAU) | Trade, Finance, Industry and Commerce | 2021-2023 |  |  |  | Guidelines and Grading tools | Number of food establishments with improved grading | Food establishments improved their grading | Reports from divisional health authorities | Divisional health authorities | Annually | Depending on food establishments in the area | Poor attitudes, resource constrains | Supportive behaviours of food establishment owners and staff to impove their standards
| Model food establishments set up ; Health promotion corner in every food establishments, Health cart concept for small scale venders, Healthy food corners (Healthy food range) |  | Formal and informal food services and food handlers, food outlets (Restaurents, canteens), street food venders | Central, Provincial, District and Divisional | Depending on the number of food industrues in the area | MoH, Provincial and district health authorities | Trade, Finance, Industry and Commerce, Fisheries, Livestocks | 2021- 2023 |  |  | Awareness programmes | Champions and role models, IEC materials, food plate cencept, Competitions | Healthy food corners in all food establishments | Healthy food concept, Healthy food corners, Healthy food promotions implemented | Observations | Divisional health authorities | Annually | Depending on formal and informal food establishments in the area | Poor attitudes, resource constrains | All food service providers compliant to promote healthy food
| Behaviour change communication programmes to promote and consume healthy foods completed |  | Food industries, Consumers | District, Divisional | 1. Depending on the number of food industrues in the area 2.At least two community awreness programmes in each PHI areas per year | Provincial and District Health authorities | Provincial and District officers from Trade, Social services, Ageiculture, fisheries and livestocks | 2021-2025 |  |  | Social marketing programmes through social media, Information hub, champhion and role models, Healtht cooking/Live talk shows, Exhibitions, Food fairs, Competitions | IEC materials, Mobile apps., Incentives for healthy foods | 1. Number of food establishments adopted healthy food promotions 2. Number of social marketing campaigns implemented | 1. Healthy food promoted adopting FBDGs 2. Dietary behavious of consumers improved | Social marketing campaigns, Periodical surveys on dietary behaviours, Reports from provincial and district authories | Divisional health and other authorities | Annually | At least 10 healthy food promotional programmes in each PHI area | Resource constrains | Social marketing/ awareness campaigns reach all layers of the community
AGRICULTURE, LIVESTOCK AND FISHERIES
Support from Agriculture, fisheries and livestocks sectors to facilitate healthy food environment for dietary behaviour change is achieved. | Advocacy programmes on; 1.Planned nutrition-sensitive agriculture, promotion of feed crop production and Seasonal forcasting 2. Improving quality of products,primary processing and storage facilities 3. Promote inland fisheries sector and marketing of fresh water fish 4. Better management of marine resources and regulation of fish harvesting 5. Improve productivity of livestock sector, Stengthen local breeds of livestocks in home-stead agriculture specially in rural and estate sectors 6. streamline the Regulatory Framework of Pesticide/Fertilizers-MGAP(Maldives Good Agricultural Practices) |  | Policy makers in agriculture, fisheries, Livestocks sectors | Central | At least one programme in each sector (Agriculture, Livestocks, Inland and Marine fisheries) per year | MoH, Trade, Law enforcement, Registrar of pestitides, SLSI | Agriculture/Fisheries/Livestocks/Rural Economic/Plantation | 2021-2022 |  |  | Advocacy programmes/meetings | Advocacy packages, Policy Briefs | Number of Advocacy programmes conducted out of scheduled | 1. Relavent national policies and stratergies amended 3. Local availability of seeds and plants, feed metarials 4. Increase of high quality fresh water and marine fish catch | Minutes, Reports on results of testing for chemical residues in water/food/meat/fish/sea food etc., SLSI, | Agriculture/Fisheries/Livestocks | Annually | 5 programmes in each sector (Agriculture, Livestocks, Inland and Marine fisheries) per year | Lack of interest due to changes in sector priorities | Policy makers have the commitment
| TOT and training programmes for farmers improve; 1. Selection of crop according to nutrition sensitive agriculture and seasonal forcasting 2. Good agriculture practices including post-harvest practices 3.Post harvesting technologies including shelf-life extension of excess agricultural products and use of by-products 4. Scale-up of Backyard farming/Home gardening (nutrient -sensitive farming) |  | Gavernment and private-sector value chain Stakeholders from producers to consumers | Central, Provincial , District | Depending on the requirement | Agriculture/Fisheries/Livestocks | Rural Economic, | 2021-2023 |  |  | , Lectures, Demonstrations | Teaching Modules, , Teaching materials | 1. Number of TOT, Training programmes conducted 2. Number of employees in agriculture, fisheries, livestocks sectors trained 3. .Number of home gardening projects supported | 1. Production of crops according to nutrition sensitive agriculture 2. compliance to good agriculture practices 3. Reduction of post-harvest losses of foods during glut period | Reports | Agriculture/Fisheries/Livestocks |  | Depending on the requirement | Lack of technical expertise, and financial resources | willingness of workers in relavent sectors to adopt nutrition sensitiv/ good agriculture practices
| Improvement of availability, acessibiltiy and affordability of nutrition sensitive agricultural products through; 1. Nutrient enhancement including bio-fortification 2. Equilty of distribution 3. Incentives and social security for producers, tax reduction and regulation of market prices |  | Producers, Vendors, Consumers/value chain Stakeholders from producers to consumers | District/Divisional |  | Agriculture, Fisheries, Livestocks,Trade and Commerce | Finance | 2021-2025 |  |  | Guidelines, Standards and Regulations |  | 1. Number of bio-fortified product introduced 2. Percentage of price change of essential food items | 1. Availabiltiy of affordable nutrition sensitive agriculture products 2. Avilability of high quality fish for consumers | Market prices |  |  |  | Lack of resources , insufficient regulatory bodies | compliance to guidelines, standards and regulations by all stakeholders in food value chain
| Consumer awareness programs through 'Good go-to-market' stratergies (healthy food buying, growing and eating) completed |  | Consumers | District/Divisional | Depending of requirement | District and divisional Agriculture, fisheires and livestocks authorities | Rural Economic/Media/Trade and Commerce/Finance | 2021-2025 |  |  | Social marketing programmes through social media, Information hub, champhion and role models, Live talk shows, Exhibitions, Food fairs | IEC materials, Mobile apps., media commercials |  | 1. Availability of diversed healthy food comodities 2. Availability of healthy covenient food 3. Consumer expenditure pattern changed (through behaviour surveillance) | Marketing and consumer Surveys |  |  |  | Lack of public interest, Compitition from commercially driven companies, Conflict of interest | Adequate support from media and public interest
Note on A4: Visakha: This is more of an assumption
Note on A5: Visakha: This is an intermediate outcome to get to the final beneficiary
Note on A23: Visakha: Which outcome in the main results frame is this related to? Thee one on availability of required food resources. Has to be linked. How does the food industry change behaviour? By provision of healthy food priducts. This is the change o in their product profile
Note on B4: Visakha: Legislation should go to Outcome 1. Settings are about BCC only
Note on B15: Visakha: Also under Outcome 1
Note on B17: Visakha: Write as a product
Note on B26: Visakha: Developing the concept is an activity
Note on I4: Visakha: Is one event.Does not continue for 1 year
Note on L4: Visakha: This is the mode of dissemination - Powerpoint presentation?video etc
Note on L15: Visakha: Pl put which MODE
Note on L16: Visakha: How?
Note on O4: Visakha: This is not descriptive of an output. There should be a distinct product like the Manual. So stated at the beginning